# Refactoring Plan & Estimation for Acorre Business API

- Framework Upgrade .NET 6 to .NET 8 (1 Week) – (In Progress – 80%)

## Analyse current codebase and architecture (80% - In Progress)

## Review Dependencies – 1 Day (50% - In Progress)

## Analyse Breaking Changes – 1 Day (50% - In Progress)

## Check Third-Party Libraries for deprecated or incompatible packages – 1 Day

## Update .NET SDK & Project Target Framework – 1 Day (100% - Completed)

## Build solution and check for changes – 1 Day (100% - Completed)

## Define coding standards and guidelines

- Code Structure & SOLID Refactoring (4 Weeks)

## Restructuring the API solution architecture – 3 Days

## Refactor Controllers - Moving business logic to service classes – 5 Days

## Implement Service & Repository Pattern - Separating business logic from data access – 5 Days

## Dependency Injection – Applying all dependencies are injected properly – 1 Day

## Interface Segregation & Abstractions - Implementing proper interfaces – 1 Day

## Separating the validation logic into validators – 2 Days

## Use string builder instead of string concatenation – 1 Day

## Removing hardcoded values – 1 Day

## Removing redundant condition checks - 1 Day

## Using Dictionaries for Quick Lookup – 1 Day

## Removal of unnecessary use of dependency injection. – 1 Day

## Removal of Nested switch statements- 3 Days

- Entity Framework Core Optimization (3 Weeks)

## Enable Lazy Loading & Eager Loading Based on Use Cases -  4 Days

## Batch Processing & Bulk Inserts and updates – 3 Days

## Removal of Untracked Queries for Read-Only Operations – 3 Days

## Eliminating unnecessary in-memory filtering – 4 Days

## Applying pagination at the database level using Skip and Take in the query – 2 Days

- Database Optimization & Query Performance (3 Weeks)

## Optimization and performance tuning for database – 3 Days

## Analyse Slow Queries – 4 Days

## Optimize SQL Queries & Joins – 2 Days

## Refactor Queries to avoid N+1 Problem – 4Days

## Prevent excessive data fetching – 2 Days

## Identify missing indexes using SQL Server Execution Plan – 1 Day

## Implement table partitioning for large datasets. – 2 Days

- Improve Maintainability, Logging & Testing (1 Week)

## Remove Dead Code & Apply Coding Standards – 3 Days

## Implement Logging – 3 Days

# Total - 12 Weeks (3 Months)